WORKING TIME AND COST  ESTIMATION AT WEST PORT JOHOR.

Scope of Work

1. Multibeam Survey

2. SingleBeam Survey at 6 rives

3. 3 Units ADCP

1. MULTIBEAM LINE SURVEY PLANING AND COSTING

1.1	SITE SURVEY

LINE SURVEY INFORMATION

ESTIMATE DEPTH RANGE: 25M

SWATH ANGLE: 90O

OVERLAP: 20%

LINE SPACING = 45M

1.2   LINE SURVEY BORDER A

LINE SPACING = 45M

TOTAL LINE= 232 LINE

TOTAL TIME SURVEY= 163HOURS

TOTAL TIME /8 HOURS = 20.3DAYS

1.3  LINE SURVEY BORDER B

LINE SPACING = 45M

TOTAL LINE= 298 LINE

TOTAL TIME SURVEY=  150 HOURS

TOTAL TIME /8 HOURS = 18.75DAYS

1.4   LINE SURVEY BORDER C

LINE SPACING = 45M

TOTAL LINE= 466 LINE

TOTAL TIME SURVEY =  101 HOURS

TOTAL TIME /8 HOURS = 12.62 DAYS

1.5  CROSS LINE

LINE SPACING = 9000M

TOTAL LINE= 5 LINE

TOTAL TIME SURVEY= 6 HOURS 44 MINUTE

TOTAL WORKING HOURS

- BORDER A = 20.3 DAYS

- BORDER B = 18.75 DAYS

- BORDER C = 12.62 DAYS

TOTAL:51.675

- CROSS LINE = 1 DAY

TOTAL WORKING HOURS =52 DAYS

TOTAL ESTIMATE SURVEY WORK FOR MBES

Survey Work        : 52 Days

Patch Test              : 6 Days

Weather Standby: 6 Days

TOTAL SURVEY DAYS = 64 DAYS

| Item | Description | Day | Qtty | Persons | Per day (RM) | Price (RM) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Mod and Demod | 60 | 1 |  | Lump Sum | 30,000 |
| 2 | Multibeam Rental Packages | 60 | 1 |  | Lump Sum | 70,000 |
|  | 2.1 Norbit Multibeam System |  |  |  |  |  |
|  | 2.2 Positining System |  |  |  |  |  |
|  | 2.3 Motion Sensor |  |  |  |  |  |
|  | 2.4 Qimara/ Qinsys |  |  |  |  |  |
| 3 | Boat Rental | 64 | 1 |  | 3000 | 192000 |
| 4 | Tide Gauge Rental | 64 | 3 |  | 200 | 38400 |
| 5 | Leveling Work |  |  |  | Lump Sum | 5000 |
| 6 | Insurance |  |  |  |  | 5000 |
| 7 | Personal | 64 |  | 4 | 400 | 102400 |
| 8 | Surveyor On Board | 6 |  | 1 | 1200 | 7200 |
| 9 | Miscellaneous (Lump Sum) |  |  |  |  | 15,000 |
| 10 | Analysis, Processing , Filtration |  |  |  |  | 10,000 |
| 11 | Endorsement from PhN and Land Surveyor |  |  |  |  | 6000 |
| 12 | Report |  |  |  |  | 10,000 |
|  | TOTAL ( RM) |  |  |  |  | 491,000 |

2.0  COST FOR MBES SURVEY FOR WEST JOHOR

2. SINGLEBEAM LINE SURVEY PLANING AND COSTING

2.1  Focus on six (6) main rivers  and coverage:

- Sungai Pendas

Line interval :50 mtr

Total line   :37 line

Required time :Apprx : 2 hours

- Sungai Perepat

Line interval :50 mtr

Total line   :26 line

Required time :Apprx : 1 hours

- Sungai Melayu

Line interval :50 mtr

Total line   : 32 line

Required time :Apprx : 2 hours 30 minutes

- Sungai Danga

Line interval :50 mtr

Total line   :53 line

Required time :Apprx : 3 hours

- Sungai Skudai

Line interval :50 mtr

Total line   : 43 line

Required time :Apprx : 4 hours

- Sungai Tebrau

Line interval :50 mtr

Total line   : 53 line

Required time :Apprx : 4 hours

6. TOTAL ESTIMATE SURVEY WORK FOR MBES

Survey Work        : 6 Days

Weather Standby: 2 Days

Mod Demod           : 3 days

TOTAL SURVEY DAYS = 11 DAYS

7.0  Cost SBES for 6 rives

| Item | Description | Day | Qtty | Persons | Per day (RM) | Price (RM) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Mod and Demod | 11 |  |  | Lump Sum | 12,000 |
| 2 | Single Beam Rental Packages | 11 |  |  | 1200 | 13200 |
|  | 2.1 Norbit Multibeam System |  |  |  |  |  |
|  | 2.2 Positining System |  |  |  |  |  |
| 3 | Boat Rental | 11 | 1 |  | 3000 | 33000 |
| 4 | Tide Gauge and levelling work |  |  |  | Lump Sum | 6000 |
| 6 | Insurance |  |  |  |  | 5000 |
| 7 | Personal | 11 |  | 4 | 350 | 15400 |
| 8 | Consumable Item |  |  |  |  | 4000 |
| 9 | Anaysis, Processing |  |  |  |  | 5000 |
| 10 | Report |  |  |  |  | 5000 |
| 12 | Endosment from PhN and Land Surveyor |  |  |  |  | 5000 |
|  |  |  |  |  |  | 103,600 |

3.0  ADCP WORK and Coasting

| Item | Description | Day | Qtty | Persons | Per day (RM) | Price (RM) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Mod and Demod | 15 |  |  | Lump Sum | 15,000 |
| 2 | ADCP Rental for (15 days) Packages | 15 | 3 |  | 600 | 27000 |
|  | 2.2 Battery |  | 3 |  | 1500 | 4500 |
| 3 | Boat Rental | 12 | 1 |  | 3000 | 36000 |
| 4 | Insurance ADCP |  |  |  | Lump Sum | 10,000 |
| 5 | Personal | 15 |  | 6 | 350 | 31500 |
| 6 | Consumable Item |  |  |  | Lump Sum | 5000 |
| 8 | Anaysis, Processing |  |  |  |  | 5000 |
| 9 | Report |  |  |  |  | 5000 |
|  |  |  |  |  |  | 139,000 |

Cost ADCP